## Slide 1: PROJECT STRUCTURE R 251102
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 2: Project structure roadmap
In whatever approach, a project should be structured
Key structural elements include:
  Project organization, which defines the roles in the project
  Project milestones, which define when decisions go/stop will be made
  Project activities which identify the project life cycles in software development, infrastructure, and organization
  Project products and deliverables
  Project work packages which define the assignments to project teams
These structural elements are needed to manage the project
The project work packages (which realize the project lifecycle) can be run according a variety of approaches: Incremental, Predictive. Hybrid
This section illustrates a roadmap to create the project structure

## Slide 3: Project Structure Roadmap
Activities
Products /deliverables
Gantt/PERT
In our roadmap, Gantt/PERT is the final step of the project structure
Organization
Milestones
In our roadmap, Gantt/PERT is the final step of the project structure

## Slide 4: PROJECT STRUCTURE
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 5: Product Breakdown Structure
Step 1
Activities
Products /deliverables
Gantt/PERT
Organization
Milestones
The Product Breakdown Structure shows the products to be released in each project domain.

## Slide 6: From Requirements to Project Products
Step 1.1 List of candidate deliverables
Step 1.2 Aggregation / Division
Step 1.3 Product Breakdown Structure
By Requirements Analysis, candidate project products are identified and listed (Step 1.1).
Then, such candidate products are aggregated or split (Step 1.2), thus obtaining the items of the Product Breakdown Structure for Software, Technology, Organization, and Security (Step 1.3).
Such Product Breakdown Structure is the portfolio (“backlog” in the Agile jargon) of products the project shall implement.

## Slide 7: Product Breakdown Structure Step 1.1 Candidate deliverables by domain
SOFTWARE (from structure diagram )
Visit reservation
Reception
GP’s diagnosis
Exam Reservation
Follow-up Visit
Health Data Warehouse and reporting
Architecture
Patient Mobile
General Practitioner
Extranet
Virtual Shared Database
Technology elements
Mobile technology
Cloud
Organization transformation
GP training
User support
Lab support
GP reward/evaluation
Organizational Business Processes
New visit /booking rules
Other key business outcomes
Manuals, Patient website
Business actions
Marketing
Contacts with GP and Hospitals
Software
Technology
Organization
Software
Technology
Organization
EXAMPLE

## Slide 8: Product Breakdown Structure Step 1.1 Candidate deliverables: comments
Deliverables can be structured in various ways :
  Area / content (like in the example)
    Software applications
    IT infrastructure
    Organization change
  User departments, e.g.:
    GP: Visit Reservation, Diagnosis, Reception, etc.
    IT department: Cloud, Virtual Shared Database, etc.
    Exam Lab: Reception. Ticket Payment
  Supplier organization e.g.:
    Systems Integrators
    Hardware / Software Vendors
    Strategic consultants
    IT department
    Human Resources Department
  Etc.

## Slide 9: Product Breakdown Structure Step 1.2 Aggregation / Division
SOFTWARE (from structure diagram )
Visit reservation 1
Reception 1
GP’s diagnosis 2
Exam Reservation 1
Follow-up Visit 1
Health Data Warehouse and reporting 3
Architecture
Patient Mobile 1
General Practitioner 2
Extranet 1
Virtual Shared Database 1
Technology elements
Mobile technology 1
Cloud 3
Organization transformation
GP training 1
User support 2
Lab support 2
GP reward/evaluation 1
Organizational Business Processes
New visit /booking rules 1
Other key business outcomes
Manuals, Patient website
Business actions
Marketing 2
Contacts with GP and Hospitals 1
Software
Technology
Organization
Software
Technology
Organization
EXAMPLE

## Slide 10: Product Breakdown Structure Step 1.3 Product List
SOFTWARE (from structure diagram )
Patient Management
  Visit reservation
  Reception
  Exam Reservation
  Follow-up Visit
GP’s diagnosis
Health Data Warehouse and reporting
New Architecture
  Patient Mobile/ Mobile technology
  Extranet
  Virtual Shared Database
General Practitioner Network
Cloud
GP
  GP training
  New visit /booking rules
  GP reward/evaluation
  Contacts with GP and Hospitals
Support
  User support
  Lab support
  Marketing
Software
Technology
Software
Technology
Organization
EXAMPLE

## Slide 11: Product Breakdown Structure Check
SOFTWARE (from structure diagram )
Backlog of software deliverables to be developed / modified/ discontinued
Services / equipment to be acquired/installed / customized/ discontinued related to
Mobile Clients, Servers
Embedded systems, Sensors
Networks
System software / middleware
Hardware Technologies
Others
Organization: structures / jobs/ roles to be changed/ created/developed:
Business Processes : processes to be created /modified/ discontinued (= Business Process Backlog)
Other key business outcomes as training, manuals, website
Business actions
Software
Technology
Organization
Software
Technology
Organization
Security
Security items to be developed /deployed/ customized modified/ discontinued
You should be sure to cover all domain items subdomains.
Hence check your draft PBS against the above checklist

## Slide 12: PBS (Product Breakdown Structure) Incident
Put down a draft PBS of the project
Just list the products you should obtain in each project domain
  Software
  Infrastructure
  Business /organization
  Other
Please consider that the relative weight of each domain varies in each project
You are free to ask information to the teacher
Hint: start from the business process (if you have already analyzed it) to sketch the products for business, software, infrastructure, etc.

## Slide 13: PROJECT STRUCTURE R 210917
  Project breakdown structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 14: Activity Breakdown Structure
Step 2
Activities
Products /deliverables
Gantt/PERT
Organization
Milestones
The Activity Breakdown Structure lists the activities to be performed for each project product.
Activities reflect the lifecycles of each project product: activities of a software product may be Waterfall or Agile or Hybrid

## Slide 15: From Project Products to Product Activities
Step 2.1 Define lifecycle models
Step 2.2 Customize / detail the lifecycle models
Step 2.2 : Define the appropriate lifecycle model for each item of the Product Breakdown Structure as listed in the following pages
  2.1.1 Software products
  2.2.2 Technology
  2.2.3 Organization
  2.2.4 Security
Step 2.2 : Detail the lifecycle model for the specific project environment

## Slide 16: From Project Products to Product Activities: 2.1.1 Software
The model for each project software product is selected (waterfall, agile, hybrid)
Patient Management
  Visit reservation (Agile)
  Reception (Agile)
  Exam Reservation (Fit-Gap)
  Follow-up Visit (Waterfall)
GP’s diagnosis (Agile)
Health Data Warehouse and reporting (Hybrid)
EXAMPLE

## Slide 17: From Project Products to Product Activities: 2.1.2 Organization
A structure for each organization product is defined
It may be created from scratch or mapped on the reference lifecycle shown here
EXAMPLE
GP
  GP training
  New visit /booking rules
  GP reward/evaluation
  Contacts with GP and Hospitals
Support
  User support
  Lab support
  Marketing
As-is Business Analysis
Interviews
To-be Business Organization Design
Change
Document Analysis
Maintenance
Structure Change
Staff Training
HR Project

## Slide 18: From Project Products to Product Activities: 2.1.3 Infrastructure
Updating
Requirements Analysis
Design of the execution architecture
Deployment
Site preparation
Test & install
Transition
Release
Maintenance
Tuning
New Architecture
  Patient Mobile/ Mobile technology
  Extranet
  Virtual Shared Database
General Practitioner Network
Cloud
EXAMPLE
An applicable structure for each infrastructure product is defined
It may be created from scratch or mapped on the reference lifecycle shown here

## Slide 19: 2.2 Customize / detail the lifecycle models
1 Software
1.1. Requirements collection & analysis
1.2 Implementation & test
1.3 Test & release
1.4 Maintenance
1.1.1 Functional
Requirements
1.1.2 Non-Functional Requirements
1.1.3 Security
Requirements
1.1.1.1 Identify users
1.1.1.2 Prepare interviews
1.1.1.3 Execute interviews
1.1.4 Model requirements
1.1.1.5 Fit gap analysis
1.1.6 Document requirements
A complete ABS breaks a project down into elementary activity, namely a task that is homogeneous in terms of output, competences, techniques. In a full detailed ABS, each elementary activity is to be described in terms of:
Input
Outcome / output
Steps of the activity
Techniques, namely the models to be used to perform the activity
Tools and software support
Best practice and examples
EXAMPLE

## Slide 20: Activity Breakdown Structure Incident
Put down a draft ABS for the software domain
You can use either Agile or Waterfall for the software backlog
You are free to ask information to the teacher
Hint: start from the PBS list and make table
  PBS element
  Approach (agile, predictive, hybrid)
  Justification of the approach

## Slide 21: PROJECT STRUCTURE R 210917
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 22: Step3 Organizing the project
Step 3 Organization
Activities
Products /deliverables
Gantt/PERT
Milestones
Project organization roles are at different levels:
Execution: teams that produce organizational, software and technology outcomes of the project
Administration: Project office, that handles communications, control and planning activities
Governance: Steering / governance structures that ensure the involvement of stakeholders and user organizations

## Slide 23: Project Organization: reference model
Project
Governance
Administration
Plan/Control
Execution
Political
Technical
Legal
Accounting
Quality
Software
Technology
Business
Organization change
Miscellaneous
Project is a temporary structure
People are involved in a project either part-time or full-time
People involved in a project play various roles:
  Governance
  Administration
  Execution

## Slide 24: Project Organization : political governance
Project
Governance
Political
Technical
Legal
Political Governance typically relies on a “Steering Committee”(SC) that includes the commissioner of the project, representative of user organizations, and, also, representatives of other stakeholders
SC typically meets monthly or at deadlines of the project
In Digital Projects, SC typically includes managers of the corporate IT department
SC is a decision body that approves or rejects project results
SC typically discusses:
  Project budget and progress
  Project staffing policy
  Project results (intermediate and final)
  Major changes in Software Apps or Organizations
  Critical issues
The project manager connects Governance with Administration and Execution organizations

## Slide 25: Project Organization: technical and legal governance
Project
Governance
Political
Technical
Legal
Technical and Legal governance make sure that project complies with relevant regulations and standards, which in digital domain typically include:
  GDPR https://eugdpr.org
  Software standards
  Deployment standards
  Accessibility standards
  Etc.
Such governance is typically staffed by “on-demand referees”, i.e., experts assigned to the project as consultants / reviewers.
In Agile / Scrum approach, specific roles as the Technical Owner make sure that software is not only consumable but also technically compliant.

## Slide 26: Project Organization : Project Administration
Project
Administration
Plan/control
Accounting
Quality
Miscellaneous
Administration supports the integration of Project Areas
Administration is performed by a Project Office (PO),which is generally staffed by non-technical people
PO typically accounts 10 to 15% of project staff

## Slide 27: Project Organization : Administration: Plan/control
Project
Administration
Plan/control
Accounting
Quality
Miscellaneous
Project planning and control is a primary mission of a PO
PO typically edits plans & reports on:
  Project Activities: baseline and updated plan, progress report, etc.
  Project Communications: project presentations for project organization and stakeholders
  Change and Risk management: make sure that changes and risks are properly documented, monitored, and solved.

## Slide 28: Project Organization : Administration: Accounting and Quality
Project
Administration
Plan/control
Accounting
Quality
Miscellaneous
Accounting:
  The project accounting team tracks expenses against the project budget, based on a specific project Cost Breakdown Structure (CBS) which is a (project) chart of accounts
  However, digital projects generally do not require a dedicated CBS, and accounting is performed as a service by the Corporate Accounting Department
Quality:
  Large projects can have quality reviewers, who make sure that the appropriate quality standards are planned and enforced.
Miscellaneous:
  In large projects, Administration can be staffed to cover all Project Management areas

## Slide 29: Project Organization : Execution
Project
Execution
Software
Technology
Business
Organization change
Execution includes the teams who develop solutions
In digital projects, relevant domains are:
  Software, where project teams develop/ customize/ discontinue/modify software apps;
  Technology, where project teams deploy software apps on cloud or internal infrastructure, and acquire / deploy software infrastructures as DBMS, OS, Drivers, etc.;
  Business, which is critical with e-commerce and social projects, where teams develop and implement business plans and models;
  Organization change, critical with enterprise digital projects, where teams design /change/discontinue business process, create/change jobs, train and sensitize users and stakeholders, etc.

## Slide 30: Project Organization : Execution: Software
Project
Execution
Software
Technology
Business
Organization change
Software teams can be structured according to a variety of models:
  Mixed teams (aka “Feature team”) where expert users, business process analysts and software developers work together - it fits customization projects
  Dedicated teams (aka ”Component teams”) , in which each team is allocated to a specific project outcome: analysis and user requirements, software development, database, etc. - it fits large waterfall projects
  Agile approach, in which multiple teams work a software product backlog, which was created in a previous analysis phase – it fits uncertain requirements with an average innovation
  Hybrid approach, a combination of the above models

## Slide 31: Project Organization : Execution: Technology
Project
Execution
Software
Technology
Business
Organization change
Dedicated technology teams exist (only) in very innovative projects
Typical enterprise or social projects develop apps on available technologies, and, therefore, rely on an external support:
  DBMS and Software Platforms vendors assist acquisition and installation
  Hardware vendors provide, install and sometimes manage hardware equipment (severs, wearable devices, sensors, etc.)
  Service vendors provide, install and operate cloud services etc.

## Slide 32: Project Organization : Execution: Business
Project
Execution
Software
Technology
Business
Organization change
Dedicated business teams are critical in e-commerce and social systems where profitability and/or social acceptance are critical success factors.
They interact with software teams in project scoping (where they contribute to shape the software product backlog) and system roll-out (where they assist the market roll-out)
Typical outcomes are business plans, marketing plans, social communication plans, surveys, etc.
Business teams typically have business administration or marketing background

## Slide 33: Project Organization : Execution: Organization Change
Project
Execution
Software
Technology
Business
Organization change
Organization change is critical in large projects, because:
  Users may be 000s
  Business process flow and activities may change radically
  Organization structure may change to a large extent
  New jobs are created and old jobs discontinued
  New skills may be required in user departments
Because of these reasons, specific teams should be created for:
  Redesigning business processes
  Redesigning business rules (e.g. chart of accounts, payment rules, etc.)
  User training, including computer-based education
  Managing HR change

## Slide 34: Project Organization : a large enterprise system project
Hardware & Software Vendors
Software Platforms
Vendors
Consultants
Systems Integrator
Software houses
Sales
Branches
Projects
Marketing
Customer
care
Network
Planning
Consumer
Division
Business
Division
Network
Systems
(OSS)
Network
Operations
Service &
Construction
IT
architecture
CRM
Development
ERP
Development
Operations
Network
VP
IT services
Other staff
CEO
Corporate user Departments
Corporate IT Department
Project
Office
Team1
Team 3
Project
Manager
Project organization
Team 2
Steering Committee
Technical Committee

## Slide 35: Project Organization : a large enterprise system project (one location)
SW development
HW & Network architecture
BPR & Change Management
Project manager
Steering Committee
Technical Committee
Business process experts
Application package experts (generally a team for each application/ application subsystem)
Database e data warehouse + Middleware experts
NB Teams are typically vendor staff
Network architects
IT Operations engineers
Hardware / software engineers
Organization analysts
HR development experts
Instructors / Coach
Representative of institutional functions that are indirectly involved in the project, e.g. Purchasing, HR, Accounting
User representatives
Supports project manager in technical issues
Reviews periodically change requests, project progress, technical issues etc.
Periodically reviews project progress
Discusses and solves issues
Decides on change requests
Approves intermediate and end results
Referees
Executive tasks of PM
Project management skills
User test skills
Project workgroup
Part time temporary task forces
IT experts
User experts
Project Administration / Office

## Slide 36: Project Organization: a multinational ERP project (multilocation)
GL
Color Print
GL
Video
GL
Corporate
Functional Experts
Functional Sub Teams
Test Sub Teams
Project Champion
(CFO)
WW Program Manager
User leader Europe
User Leader
Asia
User Leader Americas
Functional Experts
Sub Teams
+ Change control
Global bimonthly global meeting
Global Leader
Measur
Regional Deployment
Product Development

## Slide 37: Project Organization: ERP project in a large company (one location)
Engagement
Director
Engagement
Manager
Engagement
Manager / Accounting
Engagement
Manager /IT
Activities
  Coding rules (Act.1)
  Chart (Act. 2)
Role:
  Assure a top - down design
  Assure accounting consistency
  Unified Reporting
Staffing
  Consultants
  HQ
Accounting team
BI team
Program Office
IT
Software Team
Activities
  Chart (Act .3 )
  Engines (Act.5)
Role:
  Implement the consolidate Chart of Accounts customize to Divisions
Staffing
  Consultants
  Divisions
Activities
  Test new BI software
Role:
  Assess pilot engine
  Integrate SAP
Staffing
  Consultants
Activities
  Program Office
Role :
  Plan & control time and cost
  Meeting scheduling
  Document.
  Communic.
Staffing
  Consultants
  HQ
Activities
  Sofwtare Changes
  EIS-DB and ETL
  Infrastructure optimization
Role:
  Assure consistent IT infratsructure
  Install new servers
  Prepare test environment
Staffing
  IT/Development
  IT/Operation

## Slide 38: Project Organization: Incident
Put down a draft OBS of the project
You are free to ask information to the teacher
Hint: start from the PBS list
  Identify the stakeholders of each PBS backlog, who shall be represented in the project governance (Project Steering Committee or equivalent)
  Identify the possible teams for each PBS backlog, who shall be work teams in the project organization
  Draw the project organization chart
  Make sure that Privacy, Security and Legal requirements are planned and controlled in the project organization
  Make sure that all user classes (sponsor, manager of user organizations, end user, key user) are properly represented by checking the organizationn reference model

## Slide 39: PROJECT STRUCTURE R 210917
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 40: The Work Package (WP)
A project includes a plurality of WPs
A WP is an assignment an organization should accomplish

## Slide 41: Work Package (WP) properties
A WP ideally:
  Is led by 1 Organization Unit
  Produces a PBS element (1 at least)
  Addresses 1 project domain
Ideally, WPs in a project are around 10-15
Project Management is a separate WP
Other WPs address execution
A WP contains multiple Activities (= Tasks) that
  Can be realistically and confidently estimated;
  Make no sense to break down any further;
  Produce a measurable deliverable;
  Form a unique package of work which can be outsourced or contracted out.
  Are performed within a project control cycle, such as 1 month or 1 milestone

## Slide 42: Work Package (WP) comments
The WP structure can fit Agile oriented approaches
Some WPs can be implemented by an Agile approach while other WPs can be performed by a predictive approach
In an Agile approach
  the Project Management Office defines the packages
  the Agile’s Product Owner is the Organization thay leads the WP
  A WP task is roughly equivalent to a set of Sprints

## Slide 43: WP description template /1
The WP template DOES describe project elements
That WP template DOES NOT describe nor mention techniques, tools or technologies used in performing the WP
Summary
Objectives
Roles
WP
Task summary
Task details
Deliverable lists
WP Milestones

## Slide 44: WP description template / 2
WP # & Name
WP leader
Duration: from Month m to Month n
Participants & Effort per Participant (month-person or FTE)
Summary
Objectives
Roles
WP
Task summary
Task details
Deliverable lists
WP Milestones

## Slide 45: WP description template / 3
Objectives are results to be achieved
No more than 2 or 3 objectives
1-page description
Summary
Objectives
Roles
WP
Task summary
Task details
Deliverable lists
WP Milestones

## Slide 46: WP description template / 4
All the organizations involved in the work package (mentioned in the WP summary) should play a role
1-page description, with 1 line for each organization
Summary
Objectives
Roles
WP
Task summary
Task details
Deliverable lists
WP Milestones

## Slide 47: WP description template / 5
A short description of the rationale used to define and sequence tasks
Tasks should be numbered within each WP: T4.1 is Task 1 in WP4
Task summary can be supported by diagram
Summary
Objectives
Roles
WP
Task summary
Task details
Deliverable lists
WP Milestones

## Slide 48: WP description template / 6
Each task is a step in accomplishing the WP
Task detail is a 1-page description of each task in plain English
The description can be supported by a diagram
Summary
Objectives
Roles
WP
Task summary
Task details
Deliverable lists
WP Milestones

## Slide 49: WP description template / 7
The list includes all the deliverables released by WP tasks
Each task should produce a deliverable (at least one)
Deliverables are classified e.g.
  R: Document, report (excluding periodic and final reports)
  DEM: Demonstrator, pilot, prototype, plan designs
  DEC: Websites, patents filing, press & media actions, videos, etc.
  OTHER: Software, technical diagram, etc.
Deliverables should be numbered within the WP: D4.1 is deliverable 1 in WP4
Summary
Objectives
Roles
WP
Task summary
Task details
Deliverable lists
WP Milestones

## Slide 50: WP description template / 8
Each WP can be controlled by milestones = decision points where the customer decides whether to continue, repeat or stop
For each milestone you should define
  date (= month of the project as for example M06)
  deliverable (auch as D4.1 = Deliverable 4.1)
Milestones should be reported in the project Gantt and/or in a Milestone Plan
Summary
Objectives
Roles
WP
Task summary
Task details
Deliverable lists
WP Milestones

## Slide 51: WP (Work Package) Incident
Put down a draft list of WPs of Elio project
You are free to ask information to the teacher
You can sequence WPs
  Based on PBS (=outcome driven);
  Based on OBS (=organization driven);
  Based on hybrid criteria
Project WPs are ideally around 10
If you cannot reduce WPs to 10 or so, you can split the project accordingly
Detail one WP at your choice

## Slide 52: PROJECT STRUCTURE R 210917
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 53: The Gantt Diagram (WP)
Gantt diagram provides a one-page project summary by displaying WPs and related Deliverables, Milestones, Organizations
It can be modeled by various software e.g. Excel (very flexible), MS project (very powerful)

## Slide 54: Gantt diagram IRMA case study
Project Gantt diagram displays the duration and tasks of the project of WPs
In our case study Gantt diagram shows:
  WPs (blue) and related leader organization
  The tasks of each WP the leader of each WP and the related organization
  The duration of each WP and task
  The related deliverables
Our example is a DRAFT Gantt
A draft Gantt is a preliminary plan, and defines duration only

## Slide 55: Gantt diagram IRMA case study

## Slide 56: PROJECT STRUCTURE R 210917
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 57: Project Milestones
Milestones are key deadlines in a project life, where the project government either approve or reject the outcome of project work
Milestones can be at two levels
  Work package milestones concern the approval (or rejection) of a work package task
  Project milestones concern the approval (or rejection) of a whole work package or project phase
We address project milestones, and we illustrate a prototype-based milestone model, oriented to large projects.

## Slide 58: Project Milestones: a case study in financial systems
Feb
May
Jul
Aug
Jan
Mar
Apr
Jun
Sep
Nov
Oct
Dec
Sem 0
Sem 2
Sem 3
03
Functional Acceptance (= concept)
Pilot Acceptance (= small case experiment )
Approval of procedures
Authorization to invest
Order Issue
Re-planned activity
Baseline
Release I
Release II
Release III
Updated Plan
Baseline (plan used to approve and launch the project)
Project Milestones = relevant project events:
  End of project phases ;
  Reaching key objectives;
  Completion of key deliverables;
  Key decisions.
Progress
Progress against the updated plan (assessed on the actual completion (earned value))

## Slide 59: Prototype-based milestone model
We here illustrate a milestone model based on demo (prototype) and pilot phases, which is oriented to
  Large enterprise projects, where pilot and demo foster the acceptance of the system
  Research projects, where demo and prototype allow to iterate development as needed
This model fits both Waterfall, Fit-gap and Agile; indeed, Agile approach can be used within pilot and stabilization segments
Feasi-bility
(2-3 M)
Proto-type
(1-2M)
Pilot (4-6 M)
Stabili-zation
(1-3 M)
Roll-out
(variable)
Evolution

## Slide 60: Prototype-based milestones: Feasibility
Purpose: to gather technical, organizational and economic elements to decide whether to go or not to go
Characteristics:
  Organization : to be architecture
  Software: conceptual modeling (key elements) and software selection
  Technology: architecture blocks, capacity planning and partners selection
Output:
  To-be Architecture
  Project Plan
  Business Case / Cost-benefit Analysis / Impact Analysis
  Project Risk analysis
Feasi-bility
(2-3 M)
Proto-type
(1-2M)
Pilot (4-6 M)
Stabili-zation
(1-3 M)
Roll-out
(variable)
Evolution

## Slide 61: Prototype-based milestones: Prototype
Purpose: to demonstrate the future system and assess its consistency
Characteristics: the prototype demonstrates only key points
  Organization: few key points of the structure an activities
  SW: only sample functions
  Technology: integration issues / opportunities (NOT performances)
Output:
  Prototype (from a running software or a simple mock-up)
  Gap analysis (i.e., modules to be fixed / changed)
Feasi-bility
(2-3 M)
Proto-type
(1-2M)
Pilot (4-6 M)
Stabili-zation
(1-3 M)
Roll-out
(variable)
Evolution

## Slide 62: Prototype-based milestones: Pilot
Purpose: test the running solution on a sample and get a quick win
Characteristics:
  BPR and organization elements : pilot unit totally configured (typically small size, easy to change)
  Application SW: consumable
  Infrastructure: functionally complete
Output:
  Running process / system (preliminary installation)
Feasi-bility
(2-3 M)
Proto-type
(1-2M)
Pilot
(4-6 M)
Stabili-zation
(1-3 M)
Roll-out
(variable)
Evolution

## Slide 63: Prototype-based milestones: Stabilization
Stabilization
  Purpose : to remove anomalies, tune performances, refine BPR, refine adoption plan (change management & education)
  Characteristics:
    BPR and organization elements : project review
    Application software: changes (corrections & improvements ) + tuning
    Technology: tuning and fine capacity definition
  Output:
    Stabilized system
At the end of stabilization, the project team ceases
Feasi-bility
(2-3 M)
Proto-type
(1-2M)
Pilot (4-6 M)
Stabili-zation
(1-3 M)
Roll-out
(variable)
Evolution

## Slide 64: Prototype-based milestones: Roll-out
Purpose: deploy throughout the corporation / all intended users
Characteristics:
  Typical to companies geographically distributed (banks, utilities, telecoms)
  Variable duration (years in MNCs)
  Typically run by region (for example 1 region a month)
  Run by release teams guided by a release plan
Output: fully operational business process / system
Roll-out releases include training and help-desk
Feasi-bility
(2-3 M)
Proto-type
(1-2M)
Pilot
(4-6 M)
Stabili-zation
(1-3 M)
Roll-out
(variable)
Evolution

## Slide 65: Prototype-based milestones: Evolution
Purpose: the system / process fits changes arising from usage or context / technology evolution
Characteristics:
  Typically performed by periodical releases (bi-monthly or quarterly)
  Each release = a set of modified or new functions or business activities
Output: updated system / business process
Feasi-bility
(2-3 M)
Proto-type
(1-2M)
Pilot
(4-6 M)
Stabili-zation
(1-3 M)
Roll-out
(variable)
Evolution

## Slide 66: Project Milestones Incident
Put down a draft list of project milestones for Elio project or a project of your choice
You are free to ask information to the teacher
You can sequence milestones
  Based on prototype/pilot framework (illustrated before)
  Waterfall and Big-bang approach
  Any composite approach
Project milestones should be around 10
Detail one milestone at your choice

## Slide 67: PROJECT STRUCTURE R 210917
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 68: Session Summary: Project Structure Roadmap
Task Duration & Milestones
Milestones
Roles
Deliverables
Tasks
Work
Packages
Organization
Milestones
Activities
Products
Gantt

## Slide 69: Project Structure and PMBOK
PMBOK section | PBS | ABS | OBS | WP
Integration |  |  |  | 
Scope |  |  |  | 
Time |  |  |  | 
Cost |  |  |  | 
Quality |  |  |  | 
HR |  |  |  | 
Communications |  |  |  | 
Risk |  |  |  | 
Procurement |  |  |  | 
Stakeholder |  |  |  | 
Introduction
Project Domains
Project Structures
Project Work Packages
Project Milestones
Summary

## Slide 70: Review questions
Illustrate project structures
  PBS (Products / Deliverables)
  ABS (Activities)
  OBS (Organization)
  WP (Work Package)
Illustrate the purpose of a WP and the content of its sections (Heading, Objectives, Tasks, Deliverables, Roles, Milestones)
Illustrate the relations of the WP with PBS, OBS, ABS
What is a project milestone?
Illustrate the main project milestones
  Feasibility,
  Prototype,
  Pilot,
  Stabilization,
  Adoption
Introduction
Project Domains
Project Structures
Project Work Packages
Project Milestones
Summary

## Slide 71: PROJECT STRUCTURE R 210917
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 72: Assignment Assessment
The Assignment describes the Project Structure and Plan of the assigned project
The assignment is assessed in terms of:
  Completeness: all assignment sections should be developed
  Correctness: analysis / project diagrams and assignment structure should be well formed and not violate relevant syntax rules
  Readability
    Correct English
    Visible colors (no Yellow, no Light Green)
    Accessible font size

## Slide 73: Assignment structure
A scope (project) is assigned to each student team
Students’ assignment should reflect contents illustrated in the previous pages
Cover page: Name and ID of team members; Assignment release
All pages: Authors (= who oversees the page)
Step 1 From Requirements to Project Products
Step 2 From Project Products to Project Activities
Step 3 Organizing the project
Step 4 Defining project work packages
Step 5 Timelining the project
Step 6 Setting the milestones

## Slide 74: 1. Products
The Product Breakdown Structure (PBS)
  Should list the outcomes of the assigned project for Software, Infrastructure, Organization
  It may be sketched as a hierarchy or indented list
  Can contain multiple levels (hint: 2-3)
  Each product element should be specific to the assigned project, e.g.
    Patient’s Android Mobile App for Visit Management)
    Website for downloading Patient’s App
    …..
Comments on the PBS are welcome
Step 1 From Requirements to Project Products
Step 2 From Project Products to Project Activities
Step 3 Organizing the project
Step 4 Defining project work packages
Step 5 Timelining the project
Step 6 Setting the milestones

## Slide 75: 2. Product Activities
The assignment
  Should list the steps of the assigned project for each relevant Software, Technology, and Organization product
  It may be sketched as a hierarchy or indented list
  Can contain multiple levels (hint: 2-3)
  Each element should be specific to the assigned project
Comments on the structure of Product Activities are welcome
Step 1 From Requirements to Project Products
Step 2 From Project Products to Project Activities
Step 3 Organizing the project
Step 4 Defining project work packages
Step 5 Timelining the project
Step 6 Setting the milestones

## Slide 76: 3. Organization
The Organization section
  Should identify the organizations working/involved in the assigned project
  Can be described by an organization chart or an indented list
  The project organization should be consistent with PBS: each PBS element should be related to an organization unit of the project (please show that relation by a double entry table)
Step 1 From Requirements to Project Products
Step 2 From Project Products to Project Activities
Step 3 Organizing the project
Step 4 Defining project work packages
Step 5 Timelining the project
Step 6 Setting the milestones

## Slide 77: 4. Work Packages
The assignment should describe at least 2 WPs:
  Project Management
  1 WP chosen by students
The WP description should follow the Work Package template
Step 1 From Requirements to Project Products
Step 2 From Project Products to Project Activities
Step 3 Organizing the project
Step 4 Defining project work packages
Step 5 Timelining the project
Step 6 Setting the milestones

## Slide 78: 5. PERT Diagram
It shows the sequence of project Work Packages (WP), where:
  WPs should be around 10
  Project Management is WP1
  Other WPs reflect any suitable combination of Activity, Product, and Organization.
It is modeled by an oriented diagram (or graph)
The diagram is supplemented by an explanation that illustrates the concepts followed in modeling the PERT
WP 2
WP5
WP 6
WP3
WP7
WP 4
WP 1 Project Management
Example
Step 1 From Requirements to Project Products
Step 2 From Project Products to Project Activities
Step 3 Organizing the project
Step 4 Defining project work packages
Step 5 Timelining the project
Step 6 Setting the milestones

## Slide 79: 5. Gantt diagram
The Gantt diagram displays the duration of WPs and WP tasks
Gantt diagram shows:
  WPs (blue) and related leader organization
  The tasks of each WP
  The leader of each WP and his organization
  The duration of each WP and task
  The WP and task deliverables
The Gantt is a baseline, and enumerates months as “M1, M2, … “
Step 1 From Requirements to Project Products
Step 2 From Project Products to Project Activities
Step 3 Organizing the project
Step 4 Defining project work packages
Step 5 Timelining the project
Step 6 Setting the milestones

## Slide 80: B3. Milestones
Milestone | Deadline YYMMDD | Actions | Decisions to be made
Milestone 1 |  |  | 
Milestone 2 |  |  | 
……. |  |  | 
Miestone n |  |  | 
The Milestone Grid
  lists all milestones of the project
  should be consistent with PERT and WPs
  deadlines shall be relative: days/months after the day/month 0
  deadlines are to be displayed in the project Gantt
Step 1 From Requirements to Project Products
Step 2 From Project Products to Project Activities
Step 3 Organizing the project
Step 4 Defining project work packages
Step 5 Timelining the project
Step 6 Setting the milestones

## Slide 81: PROJECT STRUCTURE R 210917
  Project structure roadmap
  Step 1 From Requirements to Project Products
  Step 2 From Project Products to Project Activities
  Step 3 Organizing the project
  Step 4 Defining project work packages
  Step 5 Timelining the project
  Step 6 Setting the milestones
  Summary
  Assignment
  Appendix

## Slide 82: IRMA case study:
IRMA is integrated ecosystem to support a full range of mobility services for multiple stakeholders - municipalities, transport providers, third parties, and individuals.
Objectives :
  Information integration:
    publication of geo-referenced mobility data;
    integration of multiple sources (open data, crowd data, social network, sensor/IOT );
    structural and real time operational interoperability across geographical areas.
  Services to multiple stakeholders:
    individual users who move using multimodal transport systems;
    elderly and disabled users with specific mobility needs;
    municipalities for integrated management of long and short term, and emergency mobility, and for control of mobility related pollution;
    transport providers for the analysis of mobility flows and demand..
Scenarios:
  Pavia (targeting individual mobility services);
  Clermont-Ferrand (targeting disabled users);
  Barcelona (targeting municipal mobility services including pollution).
  International deployment: Brazil and China
Introduction
WP map
WP
description

## Slide 83: IRMA case study: WP map
IRMA’s WPS reflect both
  ABS lifecycle (Requirements, Implementation and Integration, etc.)
  OBS (Pavia, Clermont Ferrand, Barcelona, etc.)
Project Management is a separate WP
Introduction
WP map
WP
description

## Slide 84: WP Summary IRMA case study
WP #: | 4 |  |  | Start date or starting event: |  |  |  | M05 (End: M36) |  | 
WP title: | Pilot Deployment & Testing (Pavia) |  |  |  |  |  |  |  |  | 
Participant # | 1 | 2 | 3 |  | 4 | 5 | 6 |  | 7 | 8
Participant | SYS | ESP | UNIPV |  | FRANCE | MILAN | GREECE |  | ESP2 | CONS
Effort |  |  |  |  |  |  |  |  |  | 
Participant #: | 9 | 10 | 11 |  | 12 | 13 | 14 |  | 15 | 16
Participant | PAVIA | TRANSP | BLIND |  | x | x | PRC |  | BRA | 
Effort |  |  |  |  |  |  |  |  |  | 
Participant #. | Participant name | Country
1 (Coordinator) | SYS Systems Integration Company. (SYS) | Spain
2 | Supercomputing Center (ESP) | Spain
3 | Pavia University (UNIPV) | Italy
4 | French Research Lab (FRANCE) | France
5 | Milan University (MILAN) | Italy
6 | University (GREECE) | Greece
7 | Municipality (ESP2) | Spain
8 | Public Transit Consulting, S.L. (CONS) | Spain
9 | PAVIA Municipality (PAVIA) | Italy
10 | Municipal Transport Authority (TRANSP) | France
11 | Blind society (BLIND) | France
12 | Long distance (railway) transport operator | TbC
13 | Shared transport operator (car manufacturer) | TbC
14 | Institute of Technology (PRC) | China
15 | Brazlian University (BRA) | Brazil
Introduction
WP map
WP
description

## Slide 85: WP Objectives IRMA case study
1. Implement, deploy and validate services for Pavia municipality by using a wide range of information sources:
Open data: bus timetables, availability of shared bikes, street maps, indoor maps;
Crowd data: feeds from users, as feeds from dedicated collaborative applications;
Social data: tweets that are used for alert management;
Mobile network data: network events from 4G mobile radio cellular network;
Sensor data: real-time position of buses, parking lots, etc.
2. Test an interoperability data model on a sample of services.
3. Evaluate the usage profile of services in Pavia pilot by service level analysis and focus groups.
Introduction
WP map
WP
description

## Slide 86: WP Roles IRMA case study
UNIPV leads the work package.
PAVIA cooperates in validating the plan (Task 4.1) and in user test by focus groups (Task 4.2, 4.3, 4.4).
PAVIA leads Task 4.5 with the cooperation of UNIPV, that involves also SYS as a project manager.
SYS will focus on Task 4.2 that involves data on mobility taken from cells and cooperates as needed in the evaluation of technology and user impact.
Introduction
WP map
WP
description

## Slide 87: WP Tasks summary IRMA case study
The WP 4 includes two releases:
  simpler business services
  complex business services
Each release embraces the whole software lifecycle, namely:
  Development
  Test focus group: use the service, stress the software, report shortcomings and faults
  Deployment: release to Pavia end users, and deployment n the cloud.
Introduction
WP map
WP
description

## Slide 88: WP tasks detail IRMA case study
Task 4.1 Pilot plan (M05-M06, PAVIA)
The plan will detail:
  WBS (Work Breakdown Structure).
  GANTT and check points
  Reporting system on WP progress (monthly control).
  Technology infrastructure for development, test, and operation.
  The agenda of the WP
Introduction
WP map
WP
description

## Slide 89: WP tasks detail IRMA case study
Task 4.2 Pilot Services V1 (M07-M12, UNIPV)
Pavia’s Trip Planner on bus and shared bikes, and, partially, shared cars.
City Feed and Alert Manager, to process social generated feeds on transport (jams, road bumps, any mobility disruption, etc.).
Mobility Analyzer, a business intelligence application for Pavia’s Municipality, that tracks flows and delays of transport systems, and processes both real-time information and time i.e.
  Data from public transports
  Data from shared transports
  Feeds from open social network (Twitter) or community network (City Feed)
  Alerts generated by Municipality on public events
  Transit data from Municipality sensors (WIFI, Traffic jam etc.) that will be positioned in critical city points
  Aggregated traffic information on flows of vehicles and pedestrian in terms of transit time, speed and direction based on the cellular data (3G or 4G)
Introduction
WP map
WP
description

## Slide 90: WP tasks detail IRMA case study
Task 4.3 Development and Deployment of Pilot Services V2 (M13-M24, UNIPV)
Elderly services to select points of interest and itineraries for older people
Accessible routing to select accessible itineraries
Indoor Navigation, for navigation inside complex buildings, based on indoor maps and specific orientation technology (Wi-Fi, Magnetic Fields, Vision).
Reengineered Pavia’s Trip Planner to fit the interoperability data model V1.
Introduction
Project Domains
Project Structures
Project Work Packages
Project Milestones
Summary

## Slide 91: WP tasks detail IRMA case study
Task 4.4 Continuous Improvement, Operation and Maintenance (M07-M36, UNIPV) (throughout the whole WP)
Configuration and version management to make sure that original requirements, actual software implementation and deployment instructions and procedures are maintained and updated.
Continuous improvement.
  Software bugs or analysis errors are identified, evaluated and fixed.
  Improvement requests on beta versions are processed and implemented as needed (some can be implemented in the integration work package)
Task 4.5 Usage and Impact Analysis (M13-M24, PAVIA)
Focus group tests
Dashboard systems to report usage information
Introduction
WP map
WP
description

## Slide 92: WP Deliverables (1 task = 1 deliverable at least) IRMA case study
D4.1 Pavia Pilot Plan (UNIPV, R, CO, M06)
Plan of deployment and test, focus group, task details,
Data sources
D4.2 1st level services (UNIPV, DEM, PU, M12)
Downloadable App for Android
Source code
Analysis manual and User manual
Deployment guide.
D4.3 2nd level services (UNIPV, DEM, PU, M24)
The second level services rely on the common data model. They include the evidence as the first level services.
D4.4 Usage and Impact Analysis (PAV, DEC+R+DEM, PU, M24)
Dashboard software on the usage of released services, clips with interviews to key users, a report
D4.5 Final pilot report (UNIPV, R, PU, M36)
Nature keys:
R: Document, report (excluding periodic and final reports)
DEM: Demonstrator, pilot, prototype, plan designs
DEC: Websites, patents filing, press & media actions, videos, etc.
OTHER: Software, technical diagram, etc.
Dissemination keys:
PU = Public, fully open, e.g. web
CO = Confidential, restricted under conditions set out in Model Grant Agreement
CI = Classified, information as referred to in Commission Decision 2001/844/EC
Introduction
WP map
WP
description

## Slide 93: WP Milestones IRMA case study
M4.1 Pavia Pilot Plan (M06) (D4.1)
M4.2 Pilot Implementation 1 (M12) (D4.2)
M4.3 Pilot Implementation 2 (M24) (D4.5)
M4.4 End (M36) (D4.5)
A WP contains milestones, i.e. a decision point where the customer decides whether to continue, revise or stop
For each milestone are defined
  date (i.e. month of the project, e.g. M06 = 6th Month)
  deliverable (e.g. D4.1 = deliverable 4.1)
Introduction
WP map
WP
description

## Slide 94: Appendix
Project lifecycle in enterprises A case in Telecommunications

## Slide 95: Product Development Process (1/9)
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Definition of the implementation road-map
User Requirements Document Acquisition
Validation of Internal Client’s requirements
Need Classification: e.g. change request, new project, kit, etc.
Methodology and document standards usage and evidence of the meeting of the issued requirements.
The internal customer defines a product concept driven by local innovation, customers needs and market analysis
Internal customers work with IT management to support ideas and ensure completeness of requirements
Concept
Concept Definition
User requirements document acquisition
Needs classification: e. g. change request, new project, kit, etc.
User Requirement
Requests acquisition and classification
Internal customer’s requirements validation
Standard methodology and template documents to highlight requirements which can or cannot be satisfied
User requirement
refining
User requirement validation
UR = User Requirememts
PR = Product Requirements

## Slide 96: Product Development Process (2/9)
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Support the presentation of the investment request
Approval of macro- solution and effort proposed in feasibility analysis
Developing Business Metrics
The soundness and commercial rationale of the product idea are proofed via a broad business case
ARPU (Average Revenue Per Unit ) analysis and broad risk assessment are performed to establish marketing and investment gains
Going Live
-
-
Break Even
Project Costs
Customer or internal Benefit
A technical review is performed in order to identify technical constraints and evaluate technical feasibility (e.g. major impeding issues and rough costs)
IT Risks
Analysis
Costs
Analysis
Technical Involvement
Investment request approval
Macro-solution approval and booking of budget forecasted by feasibility
Definition of an implementation road-map
Project Approved
Under examination
Rejected
Development approval

## Slide 97: Product Development Process (3/9)
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Work Breakdown Structure break downs a project into several levels of work packages and tasks so to optimise process planning and control
WBS is produced by Project Manager using a top-down approach
WBS definition
Organisation Breakdown Structure identifies which work packages must be assigned to a particular sub-structure of the organisation
OBS design helps Project Manager to correctly manage and monitor project development
OBS definition
Resource Assignment Matrix is the instrument which assigns the ownerships of project work packages to people belonging to project OBS
RAM allows to univocally identify project work packages ownerships
RAM definition
Business milestones verification and prioritization of initiatives.
Verification of operational planning, IT priorities, available capacity within IT to manage the customer’s needs.
Definition of the main projects planning, based on the Customer’s priorities and IT capacity.
Identification of economical and physical resource needs
Budget Building and Allocation

## Slide 98: Product Development Process (4/9)
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Critical Path is a method to manage work packages and tasks whose completing cannot be postponed
Critical Paths can be identified by project network analysis
Critical path definition
Attività 1
Attività 2
Attività 3
Attività 4
Attività 5
Gantt Diagram allows to define project milestones and work elapsed times; it helps Project Manager to monitor project status update and to re-design project plan in case of effort updates
Gantt Design
Resources MGMT focuses on the resources effort calculation aimed to complete work package on time and on budget
Cost Planning allows to assign costs to each WP, define project budget and design costs S curve
Resources MGMT & Costs Planning
Business milestones verification and prioritization of initiatives.
Verification of operational planning, IT priorities, available capacity within IT to manage the customer’s needs.
Definition of the main projects planning, based on the Customer’s priorities and IT capacity.
Identification of economical and physical resource needs
Budget Building and Allocation

## Slide 99: Product Development Process (5/9)
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Solution definition (functional architecture)
Evaluation of technical and economic feasibility of proposed solution
Analisi
Rischi IT
Analisi
Tempi
Analisi
Costi
Modello dati
concettuale
Answers Repository
<<entity>>
answerText : BLOB
Retrieve Data()
Retrieve Answer()
Store Answer()
Schedule Answer()
Feedback Repository
<<entity>>
articleRelevance : Integer
articleUsefulness : Integer
comments : BLOB
Retrieve Data()
Store Customer Feedback()
0..n
0..n
Architecture
Costs/Benefits
Analysis
Feasibility
Compose application technical specification and perform functional quality assurance about designed technical solution
Technical Analysis
Support the definition of the solution to be implemented (functional architecture)
Evaluation of the technical/economical feasibility of the solution hypothesys

## Slide 100: Product Development Process (6/9)
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Develop product software code and perform functional quality assurance on implemented solution
Execute integration test
Perform User Acceptance Test
Check, prioritize and solve anomalies experienced during test
Solution Development
Testing
Functional support to the detailed application technical specifications
Coordination and functional quality assurance of the technical solution
Communication enabler between Users and Development departments
Functional Quality Assurance on the developed solution
Support to the user test plan engineering

## Slide 101: Product Development Process (7/9)
(23-09-10) - Pag. 101
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Plan release definition and deployment
Provide training
Perform operation support
Client tests product functionalities identifying possible issues or features not compliant with requirements
If client completely approves, product can be deployed
User Acceptance Test
Deployment
Functional Support to Integration Tests
Support during User Acceptance Tests
Support, verify and prioritization on bugs experienced during tests
Support to the design of release and deployment plan
Support to training

## Slide 102: Product Development Process (8/9)
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Overview of technical contents in order to identify stratecic and synergic implementation
Coordination of multifunxtional working teams
Identification of cross customer synergies
Definition of integrated planning approaches
Control & Manage
Synergies Identification

## Slide 103: Product Development Process (8/9)
(23-09-10) - Pag. 103
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Overview of technical contents in order to identify stratecic and synergic implementation
Coordination of multifunxtional working teams
Identification of cross customer synergies
Definition of integrated planning approaches
In accordance with Customer’s priorities, define integrated approach to avoid extra costs and useless architectural redundancy
From the very beginning, ICT Architectural Function identifies potential synergic solution in order to get an integrated approach
Architectural Review
Integrated Approach Definition

## Slide 104: Product Development Process (9/9)
Control & Manage
Synergies Identification
User
Acceptance
Development
& Test
UR/PR
Definitions
Technical
Analysis &
Business Case
Planning
Feasibility
Analysis &
Functional Specs
Planning, issues and resources analysis on several projects
Data verification and control on project approval phase and variances during project lifecycle
Problem management and definition of recovering actions (even if cross projects)
Attività 1
Attività 2
Attività 3
Attività 4
Attività 5
Control and react on milestones and activities delay, on project rescheduling
Monitor external projects impacting project plan and cooperate with external Project Manager to identify common milestones and priorities
Planning Control and Management
Resources MGMT focuses on the resources effort calculation aimed to complete work package on time and on budget
Cost Planning allows to assign costs to each WP, define project budget and design costs S curve
Resources, Costs and Project Issue/Risk Management