## Slide 1: COSTS AND BENEFITS OF DIGITAL PROJECTS R250816 - REVISED November 24th 2025
COST-BENEFIT ANALYSIS
SUMMARY AND REVIEW QUESTIONS
PROJECT BUDGET MANAGEMENT
ASSIGNMENT

## Slide 2: Analysis scope
Management approve projects based on their returns
  Returns stem from the project impact on business/organization, software, technology/infrastructure
  Returns are both financial, called “tangible”, and non-financial, called “intangible”
Our scope includes:
  The whole lifecycle of a system
  Whole project impact: tangible and intangible returns

## Slide 3: PROJECT COSTS
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 4: Software Project Costs
Analysis is the activity in which requirements are defined (modelled)
In an agile approach, analysis defines Themes / Epics of the backlog
Analysis hardly can be analytically estimated; roughly it ranges from 10% to 20% of development cost
Development
Software project
System Test
Analysis (modelling)
Miscellaneous
User Test

## Slide 5: Software Development /1
It includes costs of a development cycle, as defined by a sprint in agile approach
In predictive approaches, it includes
  Development environment
  Detailed analysis of use cases or functions (State Chart, Class Diagram)
  Coding
  Documentation
  Unit Test
Statistically, development ranges 50% to 70% of the total software cost
Development
Software project
System Test
Analysis (modelling)
Miscellaneous
User Test

## Slide 6: Software Development/2
In Agile, the development effort can be extrapolated from the number of sprints
  E.g. by assuming a sprint of 5 people x 1 month, a project with 100 sprints would require an effort of 5x100 = 500 person-month /10 =50 FTE
Alternatively, the development effort may be based on the Use-Cases, weighted in terms of Function Points (www.ifpug.org); you can find a summary on the Internet
Development
Software project
System Test
Analysis (modelling)
Miscellaneous
User Test

## Slide 7: Software Development/3: Customization
Some projects customize existing software by an editing environment or a Software Development Kit
Customization typically
  Adds new services
  Tailors existing services
  Integrates new services into the existing enterprise’s software
Costs include the development life cycle, e.g.:
  Setting of development environment
  Detailed analysis of use case or function (State Chart, Class Diagram)
  Coding
  Documentation
  Unit Test
Estimation is based on experience
Development
Software project
System Test
Analysis (modelling)
Miscellaneous
User Test

## Slide 8: System Test & User Test
System Test
  We assume that a system test is 10-20% of Development effort
  It includes integration and system test and is needed for the transition form development to production environment
  It may grow with higher risk
User Test
  It includes definition of the test case and context, expected results, documentation
  It cannot last less than one month for a significant system
  Statistically we assume that each use case or user story (= 1 elementary activity equals N use cases) requires at least 2 man-days
Development
Software project
System Test
Analysis (modelling)
Miscellaneous
User Test

## Slide 9: SOFTWARE PROJECT COST: TYPICAL BREAKDOWN
Chart: 
| Analysis | Development | Test
Colonna1 | 0.2 | 0.6 | 0.2
Software project cost
Analysis (modelling)
Development
System Test
User Test

## Slide 10: PROJECT COST – SOFTWARE
Cost Item | Algorithm | Comment
Analysis | Consulting fee * FTE | FTE are assumed as a % of SW development
Development | FTE = Sprints*5*1,2 | You can use Function Points instead of Sprints
System Test | 1/3 of development effort | Assumed as up to 1/3 of development teffor
User Test | 2 man days for each Agile Epic | User tests address how friendly and usable software is
FTE (Full Time Equivalent) = 200 days of one person
Reference cost for software engineers is 500 EUR/day = 100K for FTE (junior 250/day, mid 500/day, senior 800/day)

## Slide 11: PROJECT COSTS
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 12: Technology: Hardware
It includes the full range of hardware acquired or expanded for the project
  Mobile / Tablets
  Laptop/ Desktop
  Server
  Other equipment (router etc.)
  Sensors
  Ad hoc devices
Note:
  Purchased hardware is considered an investment and, therefore, allocated to project cost
  Rented hardware is considered as a current cost, and, therefore, is allocated to annual systems costs
Technology
LAN/ Clients /EUC
Servers
Miscellaneous
Mobile
Cloud services
Software Platform

## Slide 13: Technology: Additional hardware required by the HC project
Architecture:
  Central database with a replica
  Network for labs: extranet
  Network for mobile users: public internet
Database:
  EPR (10 M users)
  Reservations (100M records)
  Links to the HISs for referral and radiography
  Other data (DRG, Pharmacies, GP data, etc.)
MOBILE USERS Expected transactions
  Login/identification
  Query
  Reservation
  Cancellation
  Miscellaneous requests
Each mobile transaction relies on 5 microservices
Load curve of mobile users
  Monday peak:12k
  Other weekdays: 8k
  Hourly peak (9-10 am): 6k
Lab transactions:
  Patient scheduling /rescheduling
  Check-in
  Payment
  Exam assignment (2 for each check-in)
  Exam referral (2 for each check-in)
  Miscellaneous (1 for each admission)
Lab systems load:
  Admissions per day (Lombardy): 1,7M a year / 250 days = 6,8 k / day
  Hourly peak: 80% on 7-9 am = 5,5k
  No weekly peak because of schedule

## Slide 14: Technology: Cloud Services
Cloud services can concern:
  Infrastructure (IaaS): network, processing, etc.
  Software (SaaS): applications running on a cloud infrastructure.
  Platform (PasS): development environment
The cloud deployment can be:
  Private: company’s infrastructure and software are charged by some form of internal contract
  Public: cloud is run by one or more 3d-party vendors (Google, Azure, IBM, etc.)
  Hybrid: a combination of private and public cloud
Cloud services are regulated by a Service Level Agreement and controlled by a Service Level Management System
Technology
LAN/ Clients /EUC
Servers
Miscellaneous
Mobile
Cloud services
Software Platform
See Cloud on Wiki

## Slide 15: Technology: Software Platform
It includes:
  Application platform purchased or installed for the application system to be run
  Middleware platforms: DBMS, EAI, etc.
Cost includes incremental license costs:
  100% if the platform is purchased
  A percentage if the license is extended (nominal users added to an existing DBMS)
License costs typically include
  One-time license price (that is included in project cost) that can be computed as
    Absolute cost
    Cost per user or alike variable
    Absolute cost + cost per user
  Annual support fee that entitles the customer to receive assistance and support and normally account about 20 % to 10% (that is included in operational cost)
Technology
LAN/ Clients /EUC
Servers
Miscellaneous
Mobile
Cloud services
Software Platform

## Slide 16: PROJECT COST – TECHNOLOGY
Cost Item | Algorithm | Comment
EUC/LAN/Sensors | Number of users (EUC) | Depreciation on 3 years if purchased
Mobile | Number of users /agents to be equipped | Depreciation on 3 years if purchased
Servers | Expected workload | Depreciation on 3 years if purchased
Software platforms | Number of users or processing load | Annual license or upfront payment
Cloud services | Based on the expected workload | Annual service fee
User companies typically issue a request for proposal by specifying the profile of the required infrastructure
Server costs can be estimated by or using Amazon or Azure website and entering workload parameters (see the subsequent page)

## Slide 17: PROJECT COSTS
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 18: Business Project (alias Business Process Reengineering - BPR)
Analysis
  Includes
    Organizational performance analysis : KPI, Benchmarking, etc.
    Benchmarking
  Generally estimated in days by organization unit
Education /training / change
  Includes
    The out-of-pocket cost of training and education (effort + premises and rents)
    Costs of promotion, HR development, re-training and alike
  Does not include the opportunity cost of trained people
Miscellaneous
  Include contingency costs
  Contingency is typically assumed as 20% of costs
Education / Training
BPR
Analysis (modelling)
Miscellaneous

## Slide 19: PROJECT COST – BUSINESS
Cost Item | Algorithm | Comment
Analysis | Interview days * 3 | With 50 interviews = 150 consulting days
Education | A 2 day class for user group = 4 days of business consulting | With 20 user groups = 80 consulting days
Miscellaneous | Website for system promotion | Reference value can be 0,5 FTE of a business consultant
Business Consultant = 800 EUR / day = 160k FTE
Miscellaneous costs should be estimated for each specific project
Contingency costs can be added to the whole project

## Slide 20: PROJECT COSTS
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 21: Project Management
PM costs include the effort of the project manager and project office
It can be estimated as PM = D*X*R, where
  D = Effort for development + analysis
  X = Base PM percentage (10%)
  R = Risk weight as R = (100 + Risk score)/100
E.g. with
  D = 1.000
  X =10%
  R = (100+70)/100= 1,7
  PM = 1.000*10%*R = 170
Project cost
Project management
Software project
BPR
Technology

## Slide 22: PROJECT COST PROJECT MANAGEMENT
Cost Item | Algorithm | Comment
Project Office | Project total FTE *0,1 | Project office (PMO) is full time in large projects
Project management costs refers to the whole project: Software + Infrastructure + Business
10% is a reference percentage that can grow with higher project risk and complexity (please refer to the session on project risk)
Please note that PMO is a part of the project management - bare PMO can range from 5 to 15%
Consulting fee for the whole PMO staff: 800 a day = 160K /year

## Slide 23: OPERATIONS COSTS
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 24: Operations
They include the costs of operations that are added by the project
  Network services
    Additional costs of network
  Operations staff
    Additional cost of operations staff
  Energy
    Additional energy cost
  Cloud Services
    Additional cost of Cloud Services
Operations
Annual Costs
Operations staff
Energy
System Maintenance
BPR
Miscellaneous
Hw / Sw platforms
SW application
Network services

## Slide 25: Maintenance
Maintenance
  Hardware
    Annual maintenance fee for additional HW equipment
    May be assumed as 15% of the project cost
  SW platforms
    Annual fee for SW platforms
    Generally, it is 15% of acquiring cost
  Business
    Annual cost to update organization trough a periodic check up
    It may be considered as 10 % of the analysis cost
Operations
Annual Costs
Operations staff
Energy
System Maintenance
BPR
Miscellaneous
Hw / Sw platforms
SW application
Network services

## Slide 26: COST MAP
Project
Operations
Project management
Development
Software project
System Test
Analysis (modelling)
Business Project
Analysis
Technology
Mobile
LAN/ Clients/EUC
Servers
Network services
Maintenance
Business
Education/ training/ change
SW application
Operations staff
Energy
User Test
Operations
Hw / Sw platforms
Software platforms
Cloud services

## Slide 27: PROJECT BENEFITS
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 28: Where does management value come from?
Management tangible benefits are “money” and include cost saving and increased sales
Cost saving: reduction of current resource costs
  The value of saving is given by the value of resources saved in execution thanks to better efficiency and productivity
  Savings are typical (not exclusive) to the automation of existing activities
  Example: a new warehouse system
    Reduces the staff needed because picking and storing operations are performed by automated devices like Automated Guided Vehicles and computerized elevators
    Reduces stock losses by a real time inventory
ManagementValue
Tangible Benefits
Intangible
Cost saving
Increased sales

## Slide 29: Where does management value come from?
Sales growth: additional sales enabled by the system
  Increase of income thanks to the opportunity enabled by the project
  The benefit should be computed as the incremental net profit
  Examples:
    A new healthcare system attracts additional patients thus generating additional income
    A customer profiling system enables customized offering, therefore increasing sales
ManagementValue
Tangible Benefits
Intangible Benefits
Cost saving
Increased sales

## Slide 30: PROJECT BENEFITS MANAGEMENT TANGIBLE
Cost Item | Algorithm | Comment
Cost Saving | See the attached table | You should calculate the annual saving
Sales Increase | Proft on increase sales | Calculate the annual increase
SAVINGS | METRIC | APPROACH | EXAMPLE : PICKING | COMMENT
HR | Δ unit effort * expected labor price * Δ Qty | Estimate differences by stakeholder and activity | Δ unit effort : + 10 seconds Labor cost : 36 euro / hour Δ qty: 30% (less travels) on 12 M travels = 4 M | total benefit is 0,01 euro a second * 0,3*12M = 40K euro a year
SPACE | Δ Used space * Unit annual rent value | Estimate differences by resources used in each BPM lane | Δ space : 1.000 square meters Unit annual rent value : 10 euro / square meter | 1.000*10 = 10k euro / year
MATERIALS & PRODUCT | Δ qty * average value * interest rate (stock) or Δ qty * average value (usage) | Estimate differences by warehouse (stock) and by physical process | Δ stock : 1% of an average 10M euro * 10% = 100k euro Δ scrap : 5% of an average 1 M write –off = 50k euro | Stock + Scrap = 150K euro a year
EQUIPMENT | Δ qty * annual rent (or lease) or Δ annual rent | Estimate the variation on the whole architecture | No change (computer are added no saved) | The additional hardware is computed in the project cost section
SERVICE | Δ annual amount | Estimate variation by service | No change | No change
ManagementValue
Tangible Benefits
Intangible
Cost saving
Increased sales

## Slide 31: Where does management value come from?
Image/brand: it typically stems from reputation
  Measurement: survey on users
  Examples:
    Internal (Employees): a corporation provides its employees with an app that displays leaves, vacations, next assignments, company information
    External (Customers/ users): a hotel reaches a better customer’s ranking thanks to the reservation system; such benefit can be assessed by interviews, reputation analysis on social networks, statistical analysis etc.
Management Value
Tangible Benefits
Intangible Benefits
Image
QoS-KPI
Risk
Governance

## Slide 32: Where does management value come from?
QoS/KPI: better performance on time, quality, efficiency (e.g. less errors) and Quality of Service (e.g. more flexibility)
Measurement: by reporting and /or analysis
Examples
  Tracking systems enable customers to monitor their shipment and send changes or instructions to the provider or shipper
Management Value
Tangible Benefits
Intangible Benefits
Image
QoS-KPI
Risk
Governance

## Slide 33: Where does management value come from?
Governance: critical in large corporations
  Measurement: error variance and timing (faster reporting)
  Remarks: It is a main driver of management control projects and ERP in multinational corporations, where data quality is essential for management
  Example: Management control systems enable managing multilocation, multi-business and multi-plant corporations
Risk reduction: critical in banking and financial applications
  Measurement: probability x gravity
  Example: A mortgage loan system shortens the time needed to assess customer risks thanks to the integration with estate inventory, collateral evaluation, banking deposits, etc.
Management Value
Tangible Benefits
Intangible Benefits
Image
QoS-KPI
Risk
Governance

## Slide 34: PROJECT BENEFITS MANAGEMENT INTANGIBLE
Cost Item | Algorithm | Comment
Image | Ranking in terms of quality | Measurement: survey on users / customers; perceived value of the corporation
QoS/KPI | Change in error rate or improved response time | Better service KPIs raise the rank of the corporation
Governance | Improvement in reporting time and/or errors | It is a key reason for adopting an integrated management support system
Risk reduction | Change in probability and /or gravity | AI systems can enhance risk management in structured transactions
Management Value
Tangible Benefits
Intangible Benefits
Image
QoS-KPI
Risk
Governance

## Slide 35: PROJECT BENEFITS
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 36: Where does social value come from?
Social value stems from the benefits outside the enterprise, and, therefore, increases the value to customer and/or stakeholders
Tangible social benefits include:
  Social saving: reduction of the customer’s effort and/or cost in using or performing a service: e.g., buying on the internet
  Higher value: better content of the service or product enabled by the system: e.g., selection of doctor in a Health Care system
Social intangible benefits include:
  QOS/KPI: better performance of the customer’s activities in terms of time, quality, efficiency (e.g., less errors) and Quality of Service (e.g., more flexibility)
  Risk reduction: enabled by the system: e.g., a self-diagnosis enabled by a remote medical system
Social
Value
Tangible
Intangible

## Slide 37: PROJECT BENEFITS SOCIAL VALUE
Cost Item | Algorithm | Comment
Social saving | Value of activities avoided | E.g value of the time spent for avoided activities * user number (annual value)
Higher value | Increase of value received | Interviews to a focus group and mapping to the users (annual value)
QOS/KPI | Value of wider flexibility | Better performance in terms of time, quality, efficiency (e.g., less errors) and Quality of Service (e.g., more flexibility). Mapped on the user group (annual value)
Risk reduction | Risk probability * gravity | E.g. value of lower jamming probability in a traffic management system (mapped on the user group, annual value)
Social
Value
Tangible
Intangible

## Slide 38: PROJECT VALUE
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 39: PROJECT VALUE: FINANCIAL APPROACH
Financial investment evaluation addresses monetary costs and benefits (also called “return”), and relies on various algorithms:
  ROI (Return On Investment):
    How profitable is the investment?
    ROI = Average Profit / Investment * 100 = (())/n) / PC * 100
  PP (Payback Period):
    How many years are needed to pay the project investment?
    PP = Investment / Average Profit = PC/ (())/n)
  DCF (Discounted Cash Flow):
    What is the project actual value?
    In DCF, the interest «r» decreases the actual value of money over time
    DCF = Investment– Sum of discounted returns = PC – ) /

## Slide 40: PROJECT VALUE: FINANCIAL APPROACH
However, a bare financial evaluation:
  Is incomplete, since it neglects qualitative /intangible benefits that often are the very reason for a project, thus misleading project assessment;
  Is redundant, if companies consider IT projects as operational expenses (OPEX) rather than investment expenses (CAPEX) and, therefore, projects with zero return could be acceptable.
Given the limits of financial evaluation, a holistic evaluation should address the whole impact and focus on the PROJECT VALUE.

## Slide 41: PROJECT VALUE
PROJECT COSTS
SOFTWARE
PROJECT BENEFITS
MANAGEMENT VALUE
PROJECT VALUE
FINANCIAL APPROACH
INFRASTRUCTURE
BUSINESS
SOCIAL VALUE
NET VALUE APPROACH
OPERATIONS COST
OPERATIONS
SYSTEM MAINTENANCE
PROJECT MANAGEMENT

## Slide 42: NET VALUE APPROACH
Gross project / product value (V)
Tangible
Intangible
Social value (SV)
Tangible
Intangible
Management value (MV)
The gross project value V is defined as the sum of the management value MV (the sum of tangible and intangible returns for the enterprise) and the social value SV (the sum of tangible and intangible for the users), namely
V = MV + SV
The net project value V* also considers project cost (CP) & operation costs (OP) i.e.
V* = (MV+SV) – (CP+OP)

## Slide 43: NET VALUE APPROACH
Chart: Time
| Project | Y1 | Y2 | Y3 | Y4
Annual cost | 50 | 50 | 50 | 50
Benefit | 0 | 50 | 100 | 100 | 100
Project | 100
Colonna1
In our view, we consider both the project and the operation of the system/product
The related equation is
  R = PC – )
  Where:
  R is the final return of the project
  PC is the total cost of the project
  B are the annual benefits of the system
  C are the annual costs of the system
  n is the estimated duration of the system, typically 3 to 5 years
In the chart, the system operation is assumed 4 years with 1 year for the project
In year 1, benefits are reduced to 50%, to reflect a learning curve

## Slide 44: COSTS AND BENEFITS OF DIGITAL PROJECTS R250816
COST-BENEFIT ANALYSIS
SUMMARY AND REVIEW QUESTIONS
PROJECT BUDGET MANAGEMENT
ASSIGNMENT

## Slide 45: SUMMARY AND REVIEW QUESTIONS
SUMMARY
PROJECT COST
BENEFIT MAP
COST MAP
SENSITIVITY ANALYSIS
SENSITIVITY ANALYSIS
PROJECT BENEFIT
COST BENEFIT TREE
REVIEW QUESTIONS

## Slide 46: SUMMARY: THE TREE OF COSTS AND BENEFITS
Total balance
Project cost
Benefits
Costs
Annual balance
Project management
Development
Software project
System Test
Analysis (modelling)
Business Project
Analysis
Miscellanous
Technology
Mobile
LAN/ Clients/EUC
Servers
Management value
Tangible
Intangible
Social value
Tangible
Intangible
Network services
Maintenance
Business
Education/ training/ change
SW application
Operations staff
Energy
Cost saving
Sales Increase
Operations
Hw / Sw platforms
Software platforms
Cloud services
User Test

## Slide 47: Review questions: costs
Explain how to compute the software cost of a digital project.
How can you esteem infrastructure and business cost of a digital project?
How can you calculate operations and maintenance costs?
Why should the project budget also address operations and maintenance costs?

## Slide 48: Review questions: benefits
Explain what is the management value and what the social value.
Explain how you can measure tangible benefits, e.g., in manpower and stock.
Explain how you can measure intangible management benefits, e.g. in governance and risk-
Explain in which projects tangible and intangible social benefits may be critical
A system supports materials management in an automotive company: benefits are mainly managerial and tangible. Please identify benefits by using the checklist of tangible benefits.
In an e-commerce system benefits are both managerial and social. Please identify such benefits by using the checklists of tangible benefits and of social benefits.

## Slide 49: Review questions: benefits
A Business Intelligence project in a large company that profiles customers.
  A BI project for customer profiling extracts data from sales, product catalogue and market research. A good example are the marketing systems of telecommunication companies, Amazon and alike.
  That system that can require a millionaire investment is aimed at better tuning marketing, sales and assistance. Benefits are all for Management Value and stem from:
  tailored offering to business customers (e.g. small offices) with a higher capture rate = higher profit
  tailored offerings to consumers and campaign marketing = higher sales and profit
  selective assistance related to customer profile (gold, silver, bronze) = higher customer loyalty= higher profit
  Hence, benefits are pervading the whole tree of management value, both tangible and intangible. You can easily guess and specify their impact not only in terms of cost saving (less cost for the customer analysis) and sales increase (as told before) but also in terms of intangibles

## Slide 50: Review questions: benefits
A web/mobile project for citizens, that stores pension data and enables the payment of pensions.
  In this case all benefits are in the social value, since the user will have all data on its mobile and can inquire and display data of his/her pension account
A web/mobile project for tourism management stores data about resorts and supports customized visits.
  In this case benefits are in the social value, because the individual tourists can better manage their holidays, and for municipalities, which can track access and visits.

## Slide 51: SUMMARY AND REVIEW QUESTIONS
SUMMARY
BENEFIT MAP
SENSITIVITY ANALYSIS
PROJECT COST
COST BENEFIT TREE
REVIEW QUESTIONS
COST MAP
SENSITIVITY ANALYSIS
PROJECT BENEFIT

## Slide 52: PROJECT COST MAP
Project cost
Project management
Development
Software Project
System Test
Analysis (modelling)
Business Project
Analysis
Technology
Mobile
LAN/ Clients/EUC
Servers
Education/ training/ change
User Test
Software platforms
Cloud services

## Slide 53: Sensitivity assessment
Null = Less than 3%
Relevant: Between 3 and 10%
Critical: over 10%
Costs are estimated in a qualitative scale by filling the cost items
Project cost
Project management
Development
Software Project
System Test
Analysis (modelling)
Business Project
Analysis
Miscellaneous
Technology
Mobile
LAN/ Clients/EUC
Servers
Education/ training/ change
User Test
Software platforms
Cloud services

## Slide 54: PROJECT COST – ERP project Accounting in a large utility - 500 accountants
Project cost
Project management
Development
Software Project
System Test
Analysis (modelling)
Business Project
Analysis
Technology Deployment
Mobile
LAN/ Clients/EUC
Servers
Education/ change
User Test
Software platforms
Cloud services

## Slide 55: PROJECT COST – ERP PROJECT Sales + factory - 3 product divisions and 20 countries
Project cost
Project management
Development
Software Project
System Test
Analysis (modelling)
Business Project
Analysis
Miscellaneou
Technology
Mobile
LAN/ Clients/EUC
Servers
Education/ training/ change
User Test
Software platforms
Cloud services

## Slide 56: PROJECT COST – Innovative customer profiling in a large telecom with dedicated hardware
Project cost
Project management
Development
Software Project
System Test
Analysis (modelling)
Business Project
Analysis
Technology Deployment
Mobile
LAN/ Clients/EUC
Servers
Education/ change
User Test
Software platforms
Cloud services

## Slide 57: PROJECT COST MORTGAGE LOAN MANAGEMENT
Project cost
Project management
Development
Software Project
System Test
Analysis (modelling)
Business Project
Analysis
Technology Deployment
Mobile
LAN/ Clients/EUC
Servers
Education/ change
User Test
Software platforms
Cloud services

## Slide 58: PROJECT COST – HC project (Doctor)
Project cost
Project management
Development
Software Project
System Test
Analysis (modelling)
Business Project
Analysis
Technology Deployment
Mobile
LAN/ Clients/EUC
Servers
Education/ training/ change
User Test
Software platforms
Cloud services
To be filled by the students

## Slide 59: SUMMARY AND REVIEW QUESTIONS
SUMMARY
BENEFIT MAP
SENSITIVITY ANALYSIS
PROJECT COST
COST BENEFIT TREE
REVIEW QUESTIONS
COST MAP
SENSITIVITY ANALYSIS
PROJECT BENEFIT

## Slide 60: SENSITIVITY ANALYSIS
Management
Value
Social
Value
Tangible
Intangible
Cost saving
Sales Increase
Image
QoS
Risk reduction
Governance
Compliance
Social saving
Higher value
Tangible
Intangible
QOS
KPI
Benefits
Negligible
Relevant
Critical: coincides with project objectives
Benefits are estimated in a qualitative scale by filling the benefit items

## Slide 61: PROJECT BENEFITS – ERP project Accounting in a large utility - 500 accountants
Management
Value
Social
Value
Tangible
Intangible
Cost saving
Sales Increase
Image
QOS
Risk reduction
Governance
Compliance
Social saving
Higher value
Tangible
Intangible
QOS
KPI
Benefits

## Slide 62: PROJECT BENEFITS MORTGAGE LOAN MANAGEMENT
Benefits
Management
Value
Social
Value
Tangible
Intangible
Cost saving
Sales Increase
Image
QOS
Risk reduction
Governance
Compliance
Social saving
Higher value
Tangible
Intangible
QOS
KPI

## Slide 63: Potential Benefits in HC project (Doctor)
Benefits
Management
Value
Social
Value
Tangible
Intangible
Cost saving
Sales Increase
Image
QOS
Risk reduction
Governance
Compliance
Social saving
Higher value
Tangible
Intangible
QOS
KPI
To be filled by the students

## Slide 64: COSTS AND BENEFITS OF DIGITAL PROJECTS R250816
COST-BENEFIT ANALYSIS
SUMMARY AND REVIEW QUESTIONS
PROJECT BUDGET MANAGEMENT
ASSIGNMENT

## Slide 65: Summary
Cost and benefit analysis relies on 4 pillars
Business case
Cost - benefit tree
Cost management process
Cost-benefit milestones
Business case
(PMBOK)

## Slide 66: Pillar 1: Business Case
“Business Case” is an artifact of the Cost/benefit analysis
A Business Case (according to PMBOK) is a short document with the information [needed] to determine whether the project is worth the required investment, i.e.
    Business need to be served e.g.
      Request by a corporate customer (e.g., a new power station to serve a new industrial park),
      Technological advance (e.g. electronic tickets instead of paper tickets)
      Legal requirement (e.g., automation for handling toxic materials),
      Ecological impacts (e.g. energy control system)
      Social need (e.g., health care support)
    Cost-benefit analysis of the project
    Other relevant information (e.g. competition survey, benchmarking, etc.)

## Slide 67: Pillar 2: Cost and benefit items
To support the business case and project cost management, we will address:
  The whole system lifecycle
  The whole system impact
The project balance results from the project cost (“the investment”) and the costs and benefits of the system
Project balance
Project cost
System Benefits
System Cost
Management value
Social value
Maintenance
Operation

## Slide 68: Pillar 2: Cost and benefit items (cont.)
Total balance
Project cost
Benefits
Annual
Costs
Project management
Software project
Business project
Technology
Management value
Tangible
Intangible
Social value
Tangible
Intangible
Maintenance
Operations

## Slide 69: Pillar 3: Cost management
Cost Manage-ment
Plan Cost Management
Estimate Costs
Determine Budget
Control Costs
Business case evaluates project/product/system benefits at the very beginning of the project and is revised as needed
Costs are managed from the project start to end by the project office
In PMBOK, budget costs are regularly compared against actual costs

## Slide 70: Pillar 4: Cost/benefit lifecycle
Not only costs but also benefits can change during the project, thus altering the project balance
Cost- benefit analysis is to be revised/updated
  Ideally, the business case is performed at the very beginning and revised as needed in project milestones
  Ideally, cost budget is regularly updated
We here map the cost/ benefit management on a prototype-oriented project life cycle

## Slide 71: Pillar 4: Cost/benefit lifecycle (cont.)
Feasi-bility
Proto-type
Pilot
Stabili-zation
Roll-out
Evolution
Plan of project value management
Business Case
Initial Budget
Revised Business Case (as needed)
Revised Budget
Revised Business Case (as needed)
Revised Budget
Revised Business Case (as needed)
Revised Budget
Business Case closure
Project Budget closure
Maintenance budget

## Slide 72: COSTS AND BENEFITS OF DIGITAL PROJECTS R250816
COST-BENEFIT ANALYSIS
SUMMARY AND REVIEW QUESTIONS
PROJECT BUDGET MANAGEMENT
ASSIGNMENT

## Slide 73: Assignment structure
Introduction
Summary
Detail
Project Costs
Business Case
Benefits
Annual Costs
Tree
Table
Items considered
Assumptions
Values
Items considered
Assumptions
Values
Items considered
Assumptions
Values

## Slide 74: Assignment structure: Business Case
Business Case
Summary
Detail
Please list and describe in one-three pages the main needs the project should serve, typically including:
  Request by a corporate department
  Technological advance
  Legal requirement
  Ecological impacts
  Social need
  Competition /alignment to the state-of-art
A short overview of the competition or the state of art is welcome

## Slide 75: Business Case: example (GP visit)
The project stems from three business needs: technological alignmen, performannce control, social need.
Technology alignment
  AI support to GP for both anamnesis and diagnosis with dedicated systems;
  Tracking of the patient treatment and reminders;
  Implementation of a referral system;
  Multi-plaftform and multilingual
Performance control on doctors
  number of visit per day/month;
  prescribed drugs;
  prescribed therapies.
Business Case
Summary
Detail

## Slide 76: Business Case: example (GP visit)
Social need:
  GPs have the mission of prescribing drugs, making certificates, vaccines and treating wounds. Support to their practice is of utmost importance for the whole population.
  The anamnesis and diagnosis systems make it easier for doctors to understand the symptoms of a patient and, therefore, recommend the right treatment.
  A multilingual booking system makes sure that even foreigners will be able to use it seamlessly.
Business Case
Summary
Detail

## Slide 77: Summary
The summary includes
A sensitivity analysis of the tree of costs and benefits with 1-2 page of comments
The P&L statement of the project, with global value of costs and benefits
Related comments can be in the detail section
See the following page
Business Case
Summary
Detail

## Slide 78: Summary: structure
Business Case
Summary
Detail
Use colors to indicate relevance (negligible, relevant, critical)
Add one page of comments to explain your assessment
Use colors to indicate relevance (negligible, relevant, critical)
Add one page of comments to explain your assessment
Use an Excel spreadsheet
Put total value (best guess)
You can add comments but detail comments are in Detail Section

## Slide 79: Summary: Project P&L Statement (Use Excel Spreadsheet)
 | Year 0 | Year 1 | Year 2 | Year 3 | Total
PM costs |  |  |  |  | 
Software Project |  |  |  |  | 
Business project |  |  |  |  | 
Infreastructure |  |  |  |  | 
Project Costs |  |  |  |  | 
Annual savings HR (+) |  |  |  |  | 
Other savings (+) |  |  |  |  | 
Infrastructure(-) (amortization + cloud) |  |  |  |  | 
Operations (-) |  |  |  |  | 
Maintenance (-) |  |  |  |  | 
Annual Balance |  |  |  |  | 
Balance (Annual Balance – Project costs) |  |  |  |  | 
Business Case
Summary
Detail

## Slide 80: DETAIL: content
In the detail section please:
  Focus the benefit and cost items which you have identified as relevant and critical in the sensitivity maps
  Fill one spreadsheet for costs and one for benefits using the template here below
Business Case
Summary
Detail
Item decription | Algorithm | Assumptiions | Value or Coommnt